## Sheet1
|  |  | Comments | Status
Jan 11 Thursday | Jan 22 Monday | Information Architecture
Ergonomics
3D Model
3D Renders
Jan 23 Tuesday |  | Progress Presentation
Jan 23 Tuesday | Jan 25 Thursday | Wireframes
UI Basics
Jan 29 Monday |  | Progress Presentation
Jan 29 Monday | Feb 2 Friday | UI Prototyping
Product Branding and Ads space
UI animations
|  | System refine | Story boarding prep
|  | UX and HCI | List all interventions
Feb 5 Monday |  | Progress Presentation
Feb 5 Monday | Feb 9 Friday | Bill of Materials | Final Product
|  | Story Boarding | Comic strip
Sound Design
Feb 12 Monday |  | Progress Presentation
Feb 12 Monday | Feb 21 Wednesday | Final Presentation prep | Behance and IIST
Feb 22 Thursday |  | Final Presentation
Feb 22 Thursday | March 1 Friday | Final Report | Overleaf
Medium article
Academic article publishing
March 4 Monday | March 9 Friday | Project refining
Behance publishing
|  | IIIT presentation | Softboard
Internship Certificate
Letter of Recommendation